## Overview
EXECUTION PLAN V2 — $20k/month in 6 months
Day 1 = 2026-04-17 • Day 180 = 2026-10-13
MISSION | Build a 9-channel YouTube automation portfolio generating $20k/month net profit by Month 6 (Day 180).
STRATEGY | Stack three verticals: (1) Reddit story narration — highest RPM, (2) character-reaction — existing infrastructure, (3) ambient passive income. Daily cadence on all flagship channels.
THE ONE BET | Reddit Stories (Cashew) gets 50% of our attention and capital. It's the only vertical where peers at our scale earn $4k+/mo. Everything else is diversification.
TARGET KPIs
Metric | Today (Day 1) | Month 3 | Month 6 Target
Channels live with daily output | 0 | 4 | 9
Total monthly views | 0 | 400000 | 3900000
Avg RPM blended | $0 | $4.5 | $5.2
Monthly ad revenue | $0 | $1,800 | $20,000
Subscribers (summed) | 0 | 40000 | 280000
Videos published per week | 0 | 14 | 35
Channels in YPP | 0 | 2 | 7
Monthly operating costs | $20 | $65 | $180
THE 9-CHANNEL PORTFOLIO
Channel | Vertical | Launch Day | M6 Target
Reddit Stories (Cashew) | Reddit / Long-form | Day 5 | $4,200
Reddit Shorts | Reddit / Shorts | Day 20 | $900
Peanut Reacts (Sidemen) | Reaction / Long-form | Day 30 | $1,600
Peanut Reacts (KSI) | Reaction / Long-form | Day 60 | $1,600
Peanut TikTok Reacts | Reaction / Shorts | Day 45 | $1,200
HasanAbi Archive | Commentary / Long-form | Day 50 | $3,000
Reddit AITA (Pistachio) | Reddit / Long-form | Day 90 | $2,200
Cozy Ambient | Ambient / Passive | Day 75 | $1,600
Lofi Stream (24/7) | Ambient / Live | Day 100 | $800
PORTFOLIO TOTAL |  |  | $17,100 ads + diversification
PHASE BREAKDOWN
Phase | Days | Focus | Exit criteria
1. Foundation | 1-14 | Unblock Reddit scraping, ship first Reddit video, thumbnail + bg library | First Reddit video hits 1k views
2. First Channel Live | 15-28 | Daily Reddit uploads, A/B test titles/thumbs, tune for retention | Reddit Stories hits YPP (1k subs, 4k hrs)
3. Production Scaling | 29-60 | Launch Peanut Sidemen + HasanAbi Archive, add Shorts extraction | 3 channels live, combined $500/mo
4. Portfolio Build | 61-90 | Launch KSI + TikTok Reacts + Cozy Ambient + Pistachio AITA | 7 channels live, combined $3k/mo
5. Scale | 91-120 | Optimize winners, kill losers, sponsorship outreach at 50k+ | At least 1 channel at 50k subs
6. Monetization Diversification | 121-150 | Patreon, memberships, affiliates, merch on top performers | Non-AdSense revenue >$3k/mo
7. Target Hit | 151-180 | Retention work, second wave of diversification, hiring if needed | $20k/mo gross, $18k+ net
HONESTY CHECK
• Most YouTube automation attempts fail. 10-15% hit $1k/mo, ~3% hit $10k/mo at 6 months.
• $20k/mo is an aggressive target. More realistic P50: $8-12k/mo at Day 180, $20k/mo at Day 270-300.
• This plan is conservative on RPM ($5.2 blended vs niche average $8-18) — there's upside if content lands.
• Biggest single risk: YouTube's inauthentic-content policy. Avoid template-feel at all costs.
• Second biggest: Reddit API continuing to tighten. Scraping API dependency is a single point of failure.
• The plan assumes 25-40 focused hours/week on your side. Cut that in half and double every timeline.

## Revenue Model
REVENUE PROJECTION — MONTHLY GROSS (USD)
Channel | RPM ($) | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6
Reddit Stories (Cashew) | 6
└ views |  | 5000 | 50000 | 150000 | 300000 | 500000 | 700000
Reddit Shorts | 0.6
└ views |  | 20000 | 200000 | 600000 | 1200000 | 2000000 | 3000000
Peanut Reacts (Sidemen) | 4
└ views |  | 0 | 10000 | 50000 | 150000 | 300000 | 400000
Peanut Reacts (KSI) | 4
└ views |  | 0 | 0 | 10000 | 50000 | 150000 | 300000
Peanut TikTok Reacts | 0.4
└ views |  | 0 | 30000 | 200000 | 500000 | 1000000 | 1600000
HasanAbi Archive | 6
└ views |  | 0 | 20000 | 80000 | 200000 | 350000 | 500000
Reddit AITA (Pistachio) | 5
└ views |  | 0 | 0 | 0 | 30000 | 150000 | 350000
Cozy Ambient | 2
└ views |  | 0 | 0 | 50000 | 200000 | 500000 | 800000
Lofi Stream | 2
└ views |  | 0 | 0 | 0 | 50000 | 150000 | 300000
TOTAL AD REVENUE
DIVERSIFIED REVENUE
Channel memberships |  | 0 | 0 | 0 | 100 | 500 | 1500
Sponsorships (2-3 ch) |  | 0 | 0 | 0 | 0 | 1500 | 4000
Patreon |  | 0 | 0 | 0 | 50 | 200 | 600
Affiliate links |  | 0 | 0 | 20 | 80 | 200 | 500
Super Chat / Thanks |  | 0 | 0 | 10 | 50 | 150 | 400
TOTAL DIVERSIFIED
GROSS REVENUE
OPERATING COSTS
NET PROFIT
NOTES
• Blue cells = inputs. Adjust views or RPMs to stress-test. Green net-profit row recalculates automatically.
• Shorts RPM is intentionally low ($0.6 / 1k views) — Shorts pay worse than long-form. We use them for discovery not revenue.
• Sponsorship revenue only kicks in at 50k+ subs on a channel. If no channel reaches that by Month 5, zero this row.
• This model assumes 5% cost-of-revenue growth per tier (ElevenLabs + APIs scale with volume).
• Net margin at Month 6 in this model: ~99%. That's because costs are near-zero in automation. Taxes not included.

## Channel Roadmap
CHANNEL LAUNCH ROADMAP
Channel | Status | Launch Day | Launch Date | Format | Cadence | Primary Content | Dependencies
Reddit Stories (Cashew) | In dev (blocked) | 5 | 2026-04-21 | YouTube long-form 16:9 | Daily | AITA / MC / tifu / petty revenge | Reddit scraping API or OAuth
Reddit Shorts | Planned | 20 | 2026-05-06 | YouTube + TikTok 9:16, 30-60s | 3-5/day | Best moments from long-form + standalone | Long-form channel live + vertical edit script
Peanut Reacts (Sidemen) | Built, not shipping | 30 | 2026-05-16 | YouTube long-form 16:9 | 3x/week | Sidemen Among Us compilations (5-10hr) | Fix broken uk_clips (7 failed jobs)
Peanut TikTok Reacts | Config exists | 45 | 2026-05-31 | TikTok + Shorts 9:16 | Daily | Peanut reacts to viral TikToks | Source TikTok content legally + Wav2Lip/SadTalker swap
HasanAbi Archive | Built, 2 videos shipped | 50 | 2026-06-05 | YouTube long-form 16:9 | Daily | HasanAbi stream segments by topic | Source channel continuing to post + segment LLM tuning
Peanut Reacts (KSI) | Config exists | 60 | 2026-06-15 | YouTube long-form 16:9 | 3x/week | KSI reaction + commentary | Reuse Sidemen pipeline with new persona
Cozy Ambient | Config exists | 75 | 2026-06-30 | YouTube long-form | 2-3/week | 8hr rain/fireplace/cafe soundscapes | Run existing scheduler.pipelines.run_ambient_pipeline
Reddit AITA (Pistachio) | Planned | 90 | 2026-07-15 | YouTube long-form 16:9 | Daily | Different persona + subs (relationship_advice, bestofredditorupdates) | Reddit pipeline stable first
Lofi Stream (24/7) | Config exists | 100 | 2026-07-25 | YouTube 24/7 live | Continuous | Lofi beats + ambient visuals | Pick music source (AI vs licensed), RTMP setup

## Budget
MONTHLY OPERATING BUDGET (USD)
Item | Notes | M1 | M2 | M3 | M4 | M5 | M6
Hetzner VPS CPX31 | Already provisioned — 4 vCPU / 8 GB / 20 TB egress | 16 | 16 | 16 | 16 | 16 | 16
Reddit scraping API | Scrape.do free tier covers up to M4, then $30/mo | 0 | 0 | 0 | 30 | 30 | 30
ElevenLabs TTS | Free tier during MVP; upgrade to Starter at M3, Creator M5 | 0 | 0 | 22 | 22 | 99 | 99
DeepSeek LLM | ~$5-15/mo at scale; prompts are short | 2 | 5 | 8 | 10 | 15 | 15
Domain + YouTube tools | Dashboard domain, TubeBuddy Pro, vidIQ Pro | 0 | 0 | 10 | 20 | 30 | 30
Thumbnail / stock assets | Pexels free — zero cost; optional Envato $20/mo from M4 | 0 | 0 | 0 | 0 | 20 | 20
Residential proxies | Only if Reddit API path broken further | 0 | 0 | 0 | 0 | 0 | 0
Miscellaneous | Music licensing, test accounts, sponsorship research | 2 | 4 | 8 | 12 | 15 | 15
TOTAL MONTHLY COSTS
CUMULATIVE COSTS
BURN RATE NOTES
• Total 6-month spend: ~$650. Cheaper than one month of the Fal.ai OmniHuman route we rejected.
• Zero GPU cost — all GPU work (SadTalker) runs on your local RTX 4070 Laptop.
• If we pivot to GPU-cloud (Hallo2 quality upgrade) that adds $30-80/mo starting at Month 4+.
• Sponsorship revenue dwarfs all costs after Month 5 — no ROI risk if a single channel lands.

## Milestones
KEY MILESTONES
| Day | Date | Milestone | Why it matters
| 5 | 2026-04-21 | First Reddit long-form video uploaded | Validates the core pipeline end-to-end on production
| 14 | 2026-04-30 | 7 Reddit videos published, 100+ subs | Earliest signal for algorithm pickup; decides if format works
| 28 | 2026-05-14 | Reddit channel: 500 subs, 2k watch hours | Halfway to YPP — serious growth signal
| 45 | 2026-05-31 | Reddit channel monetized (YPP) | First real ad revenue — unlocks reinvestment
| 50 | 2026-06-05 | HasanAbi Archive back to daily cadence | Second revenue stream; different audience
| 60 | 2026-06-15 | $500/month across all channels | Break-even on all costs for the project
| 75 | 2026-06-30 | Cozy Ambient passive-income stream live | Set-and-forget revenue; lowest-attention channel
| 90 | 2026-07-15 | Peanut TikTok viral attempt: 1M total views | TikTok algorithm win or clear format failure
| 105 | 2026-07-30 | First sponsorship deal ($500+) | Signals channel has commercial viability
| 120 | 2026-08-14 | $3,000/month portfolio | Part-time income replacement milestone
| 135 | 2026-08-29 | At least one channel at 50k subs | Unlocks larger sponsorship tier ($1-3k/video)
| 150 | 2026-09-13 | $8,000/month — Patreon + memberships live | De-risks dependence on YouTube AdSense
| 165 | 2026-09-28 | 2+ channels with dedicated sponsorship deals | Recurring non-ad revenue
| 180 | 2026-10-13 | $20,000/month target | Goal state — 9 channels, diversified, largely hands-off

## Daily Schedule
Day | Date | Week | Month | Phase | Task | Category | Priority | Hrs | Dependencies | Status
1 | 2026-04-17 | 1 | 1 | 1. Foundation | Register Reddit app (or signup Scrape.do free tier) + add creds to .env | Infra | P0 | 0.5 |  | Not started
2 | 2026-04-18 | 1 | 1 | 1. Foundation | Wire scraping API into scheduler/reddit_pipeline.py + local test | Infra | P0 | 2 | Day 1 creds | Not started
3 | 2026-04-19 | 1 | 1 | 1. Foundation | Upload .env to VPS, pull latest, run --run-once reddit_stories end-to-end | Infra | P0 | 1.5 | Day 2 | Not started
4 | 2026-04-20 | 1 | 1 | 1. Foundation | Register Google Cloud project + create YouTube OAuth client for reddit_stories | Infra | P0 | 1 |  | Not started
5 | 2026-04-21 | 1 | 1 | 1. Foundation | Run OAuth flow, land token on VPS, trigger first real upload | Content | P0 | 1.5 | Day 4 | Not started
6 | 2026-04-22 | 1 | 1 | 1. Foundation | Observe first video performance, fix any failure modes surfaced | Analytics | P1 | 1 | Day 5 | Not started
7 | 2026-04-23 | 1 | 1 | 1. Foundation | Install systemd timer for daily 08:00 UTC scheduler run | Infra | P0 | 1 | Day 5 | Not started
8 | 2026-04-24 | 2 | 1 | 1. Foundation | Design thumbnail template (red-circle + emoji + big-text formula) | Optimization | P1 | 2 |  | Not started
9 | 2026-04-25 | 2 | 1 | 1. Foundation | Write scripts/generate_thumbnail.py (DALL-E or PIL compositing) | Optimization | P1 | 3 | Day 8 | Not started
10 | 2026-04-26 | 2 | 1 | 1. Foundation | Wire thumbnail generator into reddit_pipeline, set as YT upload thumbnail | Optimization | P1 | 1.5 | Day 9 | Not started
11 | 2026-04-27 | 2 | 1 | 1. Foundation | Download 20 free gameplay clips from Pexels + archive.org (Minecraft/Subway Surfers) | Content | P1 | 2 |  | Not started
12 | 2026-04-28 | 2 | 1 | 1. Foundation | Replace gradient background with gameplay clip rotation in composite | Optimization | P1 | 1.5 | Day 11 | Not started
13 | 2026-04-29 | 2 | 1 | 1. Foundation | Watch 3 videos of competitors (PRIVATE DIARY, Reddit Tales, Lost Genre), note format | Analytics | P2 | 1.5 |  | Not started
14 | 2026-04-30 | 2 | 1 | 1. Foundation | Week-2 retro: what works, what to cut. Push any fixes. | Analytics | P1 | 1.5 | Day 7-13 outputs | Not started
15 | 2026-05-01 | 3 | 1 | 2. First Channel | A/B test thumbnail formula A vs B on two back-to-back uploads | Optimization | P1 | 1 | thumbnails | Not started
16 | 2026-05-02 | 3 | 1 | 2. First Channel | Implement retention-based title rewriter (LLM generates 3 variants) | Optimization | P1 | 2 |  | Not started
17 | 2026-05-03 | 3 | 1 | 2. First Channel | Observe 48hr data on A/B thumbnails — keep winner formula | Analytics | P1 | 0.5 | Day 15 | Not started
18 | 2026-05-04 | 3 | 1 | 2. First Channel | Tune story truncation: aim for 9-13 min target (sweet spot for retention) | Optimization | P1 | 1 |  | Not started
19 | 2026-05-05 | 3 | 1 | 2. First Channel | Build Shorts extractor: take top moments from long-form → 60s verticals | Infra | P1 | 3 |  | Not started
20 | 2026-05-06 | 3 | 1 | 2. First Channel | LAUNCH Reddit Shorts channel: first 3 verticals uploaded manually | Content | P0 | 2 | Day 19 | Not started
21 | 2026-05-07 | 3 | 1 | 2. First Channel | Hands-off day — let algorithm do its thing, no tweaks | Rest | P2 | 0 |  | Not started
22 | 2026-05-08 | 4 | 1 | 2. First Channel | Review 7-day retention curve per video, identify drop-off patterns | Analytics | P1 | 1.5 |  | Not started
23 | 2026-05-09 | 4 | 1 | 2. First Channel | Apply retention fix: reduce intro, stronger cold-open hook | Optimization | P1 | 1.5 | Day 22 | Not started
24 | 2026-05-10 | 4 | 1 | 2. First Channel | Build analytics dashboard refresh script (daily YT Data API pull) | Analytics | P1 | 2 |  | Not started
25 | 2026-05-11 | 4 | 1 | 2. First Channel | Wire dashboard refresh into GitHub Action, runs daily 09:00 | Infra | P1 | 1 | Day 24 | Not started
26 | 2026-05-12 | 4 | 1 | 2. First Channel | Engage first 50 commenters (pin, reply, hearts) — 15 min on each channel | Marketing | P1 | 1 |  | Not started
27 | 2026-05-13 | 4 | 1 | 2. First Channel | Test monetization eligibility check via YT Studio on reddit_stories | Analytics | P1 | 0.5 |  | Not started
28 | 2026-05-14 | 4 | 1 | 2. First Channel | End of Phase 2: retro doc in docs/retros/phase2.md (metrics + learnings) | Analytics | P1 | 1 |  | Not started
29 | 2026-05-15 | 5 | 1 | 3. Production | Fix uk_clips yt-dlp + ffmpeg errors (7 historical failures in pipeline.db) | Infra | P0 | 2.5 |  | Not started
30 | 2026-05-16 | 5 | 1 | 3. Production | Run Peanut Reacts (Sidemen) pipeline on one recent playlist video end-to-end | Content | P0 | 2 | d29 | Not started
31 | 2026-05-17 | 5 | 2 | 3. Production | Upload first Sidemen reaction video to uk_clips YouTube channel | Content | P0 | 1 | d30 | Not started
32 | 2026-05-18 | 5 | 2 | 3. Production | Write scripts/rotate_character.py — same pipeline, different persona/voice | Infra | P1 | 1.5 |  | Not started
33 | 2026-05-19 | 5 | 2 | 3. Production | Dashboard: add revenue/views projection vs actual chart | Analytics | P2 | 2 |  | Not started
34 | 2026-05-20 | 5 | 2 | 3. Production | Shorts: pull 3 shorts from Sidemen reaction, upload TikTok + Shorts | Content | P1 | 1.5 | d30 | Not started
35 | 2026-05-21 | 5 | 2 | 3. Production | Daily ops: check all channel jobs succeeded overnight, fix failures | Ops | P1 | 0.5 |  | Not started
36 | 2026-05-22 | 6 | 2 | 3. Production | Watch 3 competitor recent videos, extract 3 title/thumb patterns to copy | Marketing | P2 | 1 |  | Not started
37 | 2026-05-23 | 6 | 2 | 3. Production | Re-tune LLM prompt for Reddit narration — more punchy hooks based on retention data | Optimization | P1 | 2 |  | Not started
38 | 2026-05-24 | 6 | 2 | 3. Production | Benchmark run: render 2-hour Sidemen compilation with new peanut | Content | P1 | 3 |  | Not started
39 | 2026-05-25 | 6 | 2 | 3. Production | Upload compilation to uk_clips, schedule for 9am next morning | Content | P1 | 0.5 | d38 | Not started
40 | 2026-05-26 | 6 | 2 | 3. Production | Start HasanAbi Archive daily cadence (fix any bugs blocking d10-14 production) | Content | P0 | 2 |  | Not started
41 | 2026-05-27 | 6 | 2 | 3. Production | Daily ops + engagement — reply to top 10 comments on each active channel | Marketing | P1 | 1 |  | Not started
42 | 2026-05-28 | 6 | 2 | 3. Production | A/B test: peanut-in-frame vs no-peanut on Reddit Shorts (visual variant test) | Optimization | P1 | 1.5 |  | Not started
43 | 2026-05-29 | 7 | 2 | 3. Production | Measure CTR improvement from thumbnail v2 vs v1 across 10-video window | Analytics | P1 | 1 |  | Not started
44 | 2026-05-30 | 7 | 2 | 3. Production | Write channel-specific posting schedule doc + set YT premieres | Ops | P1 | 1 |  | Not started
45 | 2026-05-31 | 7 | 2 | 3. Production | Light day — measurement + community replies only | Rest | P2 | 0.5 |  | Not started
46 | 2026-06-01 | 7 | 2 | 3. Production | Sidemen compilation performance review at 72hr (views, retention, CTR) | Analytics | P1 | 1 | d38 upload | Not started
47 | 2026-06-02 | 7 | 2 | 3. Production | Generate next batch of Reddit narrations offline (seed 7 days of content) | Content | P1 | 2.5 |  | Not started
48 | 2026-06-03 | 7 | 2 | 3. Production | Research + note 3 mid-tier competitors' sponsorship deals (Skillshare, BetterHelp, etc.) | Marketing | P2 | 1 |  | Not started
49 | 2026-06-04 | 7 | 2 | 3. Production | Daily ops + spot-check oldest videos still getting views (evergreen signal) | Ops | P1 | 0.5 |  | Not started
50 | 2026-06-05 | 8 | 2 | 3. Production | Dashboard: add per-channel RPM tracking (pulled from YT Studio) | Analytics | P2 | 1.5 |  | Not started
51 | 2026-06-06 | 8 | 2 | 3. Production | Implement emotion-aware TTS chunking: slow down for shocks, speed up for rants | Optimization | P2 | 2 |  | Not started
52 | 2026-06-07 | 8 | 2 | 3. Production | Shorts cadence bump: 5/day on Reddit Shorts if engagement holds | Content | P1 | 1.5 |  | Not started
53 | 2026-06-08 | 8 | 2 | 3. Production | Hands-off observation day | Rest | P2 | 0 |  | Not started
54 | 2026-06-09 | 8 | 2 | 3. Production | Write a post-mortem on any videos that flopped (<500 views) this week | Analytics | P1 | 1.5 |  | Not started
55 | 2026-06-10 | 8 | 2 | 3. Production | Polish facecam layout on Peanut Reacts — bigger peanut, better positioning | Optimization | P2 | 1.5 |  | Not started
56 | 2026-06-11 | 8 | 2 | 3. Production | End of Phase 3 sprint: land Sidemen, HasanAbi, Reddit Stories all at daily cadence | Ops | P0 | 2 |  | Not started
57 | 2026-06-12 | 9 | 2 | 3. Production | Big retrospective — rank channels by ROI (time spent vs $/views) | Analytics | P0 | 2.5 |  | Not started
58 | 2026-06-13 | 9 | 2 | 3. Production | Kill underperforming content formats based on retro; invest in winners | Optimization | P0 | 1.5 | d58 | Not started
59 | 2026-06-14 | 9 | 2 | 3. Production | Write content calendar for Month 3 based on Phase-3 learnings | Ops | P1 | 1.5 |  | Not started
60 | 2026-06-15 | 9 | 2 | 3. Production | Month 2 milestone check: $500/mo target across channels? | Analytics | P0 | 1 |  | Not started
61 | 2026-06-16 | 9 | 3 | 4. Portfolio | Spin up Peanut Reacts (KSI) — clone Sidemen pipeline with new persona/voice | Infra | P1 | 3 |  | Not started
62 | 2026-06-17 | 9 | 3 | 4. Portfolio | Upload first KSI reaction to peanut_ksi channel | Content | P0 | 1.5 | d61 | Not started
63 | 2026-06-18 | 9 | 3 | 4. Portfolio | Scale Reddit Shorts to 5/day — push automation to handle higher volume | Infra | P1 | 2 |  | Not started
64 | 2026-06-19 | 10 | 3 | 4. Portfolio | Measure TikTok vs YouTube Shorts on same clip — which platform wins? | Analytics | P1 | 1 |  | Not started
65 | 2026-06-20 | 10 | 3 | 4. Portfolio | Launch Peanut TikTok Reacts channel: 3 uploads to seed algorithm | Content | P0 | 2 |  | Not started
66 | 2026-06-21 | 10 | 3 | 4. Portfolio | Daily ops + algorithm observation (focus: is content getting impressions?) | Ops | P1 | 0.75 |  | Not started
67 | 2026-06-22 | 10 | 3 | 4. Portfolio | Light day — community replies, trending topic research | Marketing | P2 | 1 |  | Not started
68 | 2026-06-23 | 10 | 3 | 4. Portfolio | Tune KSI reaction script: more kinetic hooks, faster pacing | Optimization | P1 | 1.5 |  | Not started
69 | 2026-06-24 | 10 | 3 | 4. Portfolio | Research ambient/lofi channel music licensing (Epidemic Sound vs Royalty Free) | Marketing | P1 | 1.5 |  | Not started
70 | 2026-06-25 | 10 | 3 | 4. Portfolio | Launch Cozy Ambient channel: 1st 8-hour rain video | Content | P0 | 2 |  | Not started
71 | 2026-06-26 | 11 | 3 | 4. Portfolio | Measure first KSI video 72hr performance vs Sidemen baseline | Analytics | P1 | 1 |  | Not started
72 | 2026-06-27 | 11 | 3 | 4. Portfolio | Scale Reddit Stories to 2 videos/day (experiment — stop if CTR drops) | Content | P1 | 1.5 |  | Not started
73 | 2026-06-28 | 11 | 3 | 4. Portfolio | Build weekly sponsor outreach tracker sheet + CRM template | Marketing | P1 | 1.5 |  | Not started
74 | 2026-06-29 | 11 | 3 | 4. Portfolio | Daily ops | Ops | P2 | 0.75 |  | Not started
75 | 2026-06-30 | 11 | 3 | 4. Portfolio | Monitor at-risk channels (<1k subs month-over-month flat) | Analytics | P1 | 1 |  | Not started
76 | 2026-07-01 | 11 | 3 | 4. Portfolio | Test LLM persona variation on Reddit Stories — measure CTR impact | Optimization | P1 | 2 |  | Not started
77 | 2026-07-02 | 11 | 3 | 4. Portfolio | Submit TikTok Reacts to TikTok Creator Fund (requires 10k followers) | Marketing | P1 | 0.5 |  | Not started
78 | 2026-07-03 | 12 | 3 | 4. Portfolio | Peanut KSI second upload — adjust based on first-video retention data | Content | P1 | 1.5 |  | Not started
79 | 2026-07-04 | 12 | 3 | 4. Portfolio | Add Shorts extractor to KSI + Sidemen (Shorts per long-form = 3-5) | Infra | P1 | 2 |  | Not started
80 | 2026-07-05 | 12 | 3 | 4. Portfolio | Build auto-reply bot for FAQ comments across channels | Optimization | P2 | 2 |  | Not started
81 | 2026-07-06 | 12 | 3 | 4. Portfolio | Light day — observe portfolio, no code changes | Rest | P2 | 0.5 |  | Not started
82 | 2026-07-07 | 12 | 3 | 4. Portfolio | Week retro on Month 3 progress vs plan — rebaseline if >20% off | Analytics | P0 | 1.5 |  | Not started
83 | 2026-07-08 | 12 | 3 | 4. Portfolio | Launch Reddit AITA (Pistachio) — different persona, different subs focus | Content | P0 | 2.5 |  | Not started
84 | 2026-07-09 | 12 | 3 | 4. Portfolio | Content calendar: 30 days ahead for each channel, spread topics | Ops | P1 | 2 |  | Not started
85 | 2026-07-10 | 13 | 3 | 4. Portfolio | Daily ops | Ops | P2 | 0.75 |  | Not started
86 | 2026-07-11 | 13 | 3 | 4. Portfolio | Benchmark: total portfolio monthly RPM vs niche average ($8-18) | Analytics | P1 | 1 |  | Not started
87 | 2026-07-12 | 13 | 3 | 4. Portfolio | Hit rate-limit issue workarounds (Reddit API, TTS, DeepSeek) | Ops | P1 | 1.5 |  | Not started
88 | 2026-07-13 | 13 | 3 | 4. Portfolio | Sponsorship outreach: reach out to 5 mid-tier brands relevant to Reddit Stories | Marketing | P1 | 2 |  | Not started
89 | 2026-07-14 | 13 | 3 | 4. Portfolio | Observe responses — adjust pitch deck based on first-contact signal | Marketing | P1 | 1 |  | Not started
90 | 2026-07-15 | 13 | 3 | 4. Portfolio | End of Month 3: milestone review — are we on track for $3k/mo at d120? | Analytics | P0 | 2 |  | Not started
91 | 2026-07-16 | 13 | 4 | 5. Scale | Upgrade top-performing channel to higher-quality TTS (ElevenLabs Creator) | Optimization | P1 | 1 |  | Not started
92 | 2026-07-17 | 14 | 4 | 5. Scale | Fund ElevenLabs Creator tier ($99/mo) if ROI clear on top channel | Ops | P1 | 0.25 |  | Not started
93 | 2026-07-18 | 14 | 4 | 5. Scale | Build template for mid-tier sponsorship emails — personalize + send 10/week | Marketing | P1 | 2 |  | Not started
94 | 2026-07-19 | 14 | 4 | 5. Scale | Daily ops + community management (30 min per channel) | Ops | P1 | 2 |  | Not started
95 | 2026-07-20 | 14 | 4 | 5. Scale | Identify channel with highest RPM × view velocity — double down | Analytics | P0 | 1.5 |  | Not started
96 | 2026-07-21 | 14 | 4 | 5. Scale | Start Lofi 24/7 stream on lofi_vibes — RTMP setup + music source | Infra | P0 | 3 |  | Not started
97 | 2026-07-22 | 14 | 4 | 5. Scale | Measure Lofi retention first 48 hours (watch hours is the KPI) | Analytics | P1 | 1 |  | Not started
98 | 2026-07-23 | 14 | 4 | 5. Scale | Sponsorship follow-ups on last week's cold-out outreach | Marketing | P1 | 1 |  | Not started
99 | 2026-07-24 | 15 | 4 | 5. Scale | Review+kill: 2 weakest channels if trajectory clearly bad (<500 subs at d100) | Optimization | P0 | 1.5 |  | Not started
100 | 2026-07-25 | 15 | 4 | 5. Scale | Redirect effort from killed channels to top 2 winners | Ops | P0 | 1 |  | Not started
101 | 2026-07-26 | 15 | 4 | 5. Scale | Build Patreon page for top channel — tiers, benefits, copy | Marketing | P1 | 3 |  | Not started
102 | 2026-07-27 | 15 | 4 | 5. Scale | Announce Patreon in a pinned comment on top 10 videos + end cards | Marketing | P1 | 1.5 |  | Not started
103 | 2026-07-28 | 15 | 4 | 5. Scale | Enable channel memberships on eligible channels (need 1k subs) | Marketing | P1 | 1 |  | Not started
104 | 2026-07-29 | 15 | 4 | 5. Scale | Light day — observe Patreon + memberships signals | Rest | P2 | 0.5 |  | Not started
105 | 2026-07-30 | 15 | 4 | 5. Scale | Sidemen compilation v2: 6-hour version (longer = higher watch time) | Content | P1 | 3 |  | Not started
106 | 2026-07-31 | 16 | 4 | 5. Scale | Upload, set as premiere with live chat | Content | P1 | 0.5 |  | Not started
107 | 2026-08-01 | 16 | 4 | 5. Scale | Daily ops | Ops | P2 | 0.75 |  | Not started
108 | 2026-08-02 | 16 | 4 | 5. Scale | Optimize Reddit Stories CPM: target higher-RPM demographics (US/UK) | Optimization | P1 | 1.5 |  | Not started
109 | 2026-08-03 | 16 | 4 | 5. Scale | Add English-US preferred-language meta to uploads | Optimization | P2 | 0.5 |  | Not started
110 | 2026-08-04 | 16 | 4 | 5. Scale | Launch first affiliate link in description (Audible, Skillshare, etc.) | Marketing | P1 | 1 |  | Not started
111 | 2026-08-05 | 16 | 4 | 5. Scale | Daily ops + sponsor follow-ups | Ops | P1 | 1 |  | Not started
112 | 2026-08-06 | 16 | 4 | 5. Scale | Diversify Reddit source: add r/relationship_advice, r/bestofredditorupdates | Content | P1 | 1 |  | Not started
113 | 2026-08-07 | 17 | 4 | 5. Scale | A/B test long (15 min) vs longer (25 min) Reddit Stories — watch-time impact? | Optimization | P1 | 1.5 |  | Not started
114 | 2026-08-08 | 17 | 4 | 5. Scale | Make winning length the default; update content generator | Ops | P1 | 1 |  | Not started
115 | 2026-08-09 | 17 | 4 | 5. Scale | Sponsorship pipeline review — follow up all open threads | Marketing | P1 | 1 |  | Not started
116 | 2026-08-10 | 17 | 4 | 5. Scale | Portfolio dashboard refresh: revenue, views, subs, trendlines | Analytics | P1 | 1.5 |  | Not started
117 | 2026-08-11 | 17 | 4 | 5. Scale | Light day | Rest | P2 | 0.5 |  | Not started
118 | 2026-08-12 | 17 | 4 | 5. Scale | First sponsorship signed (target) | Marketing | P0 | 1 |  | Not started
119 | 2026-08-13 | 17 | 4 | 5. Scale | Sponsor video production + delivery per contract | Content | P1 | 2.5 |  | Not started
120 | 2026-08-14 | 18 | 4 | 5. Scale | Month 4 retro — burn-rate vs revenue curve reality check | Analytics | P0 | 2 |  | Not started
121 | 2026-08-15 | 18 | 5 | 6. Diversify | Review all diversified revenue streams — which pay, which don't | Analytics | P0 | 1.5 |  | Not started
122 | 2026-08-16 | 18 | 5 | 6. Diversify | Double down on best-performing diversification lever | Ops | P1 | 1 |  | Not started
123 | 2026-08-17 | 18 | 5 | 6. Diversify | Merch ideation: simple design, Printful/Teespring (character-branded) | Marketing | P2 | 2 |  | Not started
124 | 2026-08-18 | 18 | 5 | 6. Diversify | Launch merch store, link in descriptions | Marketing | P2 | 1.5 |  | Not started
125 | 2026-08-19 | 18 | 5 | 6. Diversify | Patreon content exclusives — 1 bonus video/week for top tier | Content | P1 | 2 |  | Not started
126 | 2026-08-20 | 18 | 5 | 6. Diversify | Super Thanks enabled on all monetized channels | Ops | P1 | 0.5 |  | Not started
127 | 2026-08-21 | 19 | 5 | 6. Diversify | Analyze YouTube Premium revenue share per channel — optimize for it | Analytics | P2 | 1 |  | Not started
128 | 2026-08-22 | 19 | 5 | 6. Diversify | Second sponsorship — larger deal with mid-tier advertiser | Marketing | P0 | 1.5 |  | Not started
129 | 2026-08-23 | 19 | 5 | 6. Diversify | Daily ops + content | Ops | P2 | 1 |  | Not started
130 | 2026-08-24 | 19 | 5 | 6. Diversify | Shorts repurposing to IG Reels + TikTok (cross-platform) | Content | P1 | 2 |  | Not started
131 | 2026-08-25 | 19 | 5 | 6. Diversify | Measure cross-platform traffic / growth | Analytics | P1 | 1 |  | Not started
132 | 2026-08-26 | 19 | 5 | 6. Diversify | Affiliate stack: add 2nd and 3rd products to top channel descriptions | Marketing | P1 | 1 |  | Not started
133 | 2026-08-27 | 19 | 5 | 6. Diversify | Observation day — let things run, just monitor | Rest | P2 | 0.25 |  | Not started
134 | 2026-08-28 | 20 | 5 | 6. Diversify | Build a weekly report script: net revenue, cost, top videos, actions | Analytics | P1 | 2.5 |  | Not started
135 | 2026-08-29 | 20 | 5 | 6. Diversify | Publish first weekly report, use it to drive next week | Analytics | P1 | 0.5 |  | Not started
136 | 2026-08-30 | 20 | 5 | 6. Diversify | Expand Cozy Ambient — test 12-hour ASMR sleep variant | Content | P2 | 2 |  | Not started
137 | 2026-08-31 | 20 | 5 | 6. Diversify | Sponsorship deal #3 — target tier-two advertiser | Marketing | P0 | 1.5 |  | Not started
138 | 2026-09-01 | 20 | 5 | 6. Diversify | Evaluate hiring a part-time VA for comment management + research | Ops | P1 | 1 |  | Not started
139 | 2026-09-02 | 20 | 5 | 6. Diversify | Sidemen mega-compilation: 10-hour version | Content | P1 | 3.5 |  | Not started
140 | 2026-09-03 | 20 | 5 | 6. Diversify | Upload + premiere schedule | Content | P1 | 0.5 |  | Not started
141 | 2026-09-04 | 21 | 5 | 6. Diversify | Daily ops | Ops | P2 | 0.75 |  | Not started
142 | 2026-09-05 | 21 | 5 | 6. Diversify | Hit $8k/mo milestone check — course-correct if not on track | Analytics | P0 | 1.5 |  | Not started
143 | 2026-09-06 | 21 | 5 | 6. Diversify | Write case-study doc to pitch future sponsors (numbers + audience) | Marketing | P1 | 2 |  | Not started
144 | 2026-09-07 | 21 | 5 | 6. Diversify | Reach out to agency that reps multi-channel creators | Marketing | P1 | 1 |  | Not started
145 | 2026-09-08 | 21 | 5 | 6. Diversify | Review algorithm changes this past month — any ranking shifts? | Analytics | P1 | 1 |  | Not started
146 | 2026-09-09 | 21 | 5 | 6. Diversify | Optimize thumbnails on top 20 videos (highest-traffic get refresh) | Optimization | P1 | 2 |  | Not started
147 | 2026-09-10 | 21 | 5 | 6. Diversify | Light day | Rest | P2 | 0.5 |  | Not started
148 | 2026-09-11 | 22 | 5 | 6. Diversify | Record behind-the-scenes / making-of video (fan-funnel content) | Content | P2 | 2 |  | Not started
149 | 2026-09-12 | 22 | 5 | 6. Diversify | Publish BTS on top channel + Patreon tease | Content | P2 | 0.5 |  | Not started
150 | 2026-09-13 | 22 | 5 | 6. Diversify | Phase 6 retro — diversification: what's the multiplier on ad revenue now? | Analytics | P0 | 2 |  | Not started
151 | 2026-09-14 | 22 | 6 | 7. Target Hit | Set the $20k target visibly — daily dashboard check | Ops | P0 | 0.25 |  | Not started
152 | 2026-09-15 | 22 | 6 | 7. Target Hit | Analyze: which channels are still accelerating, which plateaued? | Analytics | P0 | 2 |  | Not started
153 | 2026-09-16 | 22 | 6 | 7. Target Hit | Pour extra content budget on accelerating ones (more videos/week) | Ops | P1 | 1 |  | Not started
154 | 2026-09-17 | 22 | 6 | 7. Target Hit | Third sponsorship tier — longer deals (quarterly), higher rates | Marketing | P0 | 2 |  | Not started
155 | 2026-09-18 | 23 | 6 | 7. Target Hit | Daily ops + community | Ops | P1 | 0.75 |  | Not started
156 | 2026-09-19 | 23 | 6 | 7. Target Hit | Consolidate best tactics doc — what consistently works | Analytics | P1 | 2 |  | Not started
157 | 2026-09-20 | 23 | 6 | 7. Target Hit | Test premium video format on top channel (fancier visuals / guest voice) | Content | P1 | 3 |  | Not started
158 | 2026-09-21 | 23 | 6 | 7. Target Hit | Measure premium format lift | Analytics | P1 | 1 |  | Not started
159 | 2026-09-22 | 23 | 6 | 7. Target Hit | Expand video library — 2 videos/day on reddit_stories during sprint | Content | P1 | 1.5 |  | Not started
160 | 2026-09-23 | 23 | 6 | 7. Target Hit | Observation day | Rest | P2 | 0.25 |  | Not started
161 | 2026-09-24 | 23 | 6 | 7. Target Hit | Premium email newsletter for super-fans (Substack / Convertkit) | Marketing | P2 | 2.5 |  | Not started
162 | 2026-09-25 | 24 | 6 | 7. Target Hit | Announce newsletter on all channels — build owned audience | Marketing | P1 | 0.5 |  | Not started
163 | 2026-09-26 | 24 | 6 | 7. Target Hit | Daily ops | Ops | P2 | 0.75 |  | Not started
164 | 2026-09-27 | 24 | 6 | 7. Target Hit | Auto-publish schedule audit — ensure all 9 channels have 30-day queue | Ops | P1 | 2 |  | Not started
165 | 2026-09-28 | 24 | 6 | 7. Target Hit | YouTube Partner Manager outreach (if >250k subs on any channel) | Marketing | P1 | 1 |  | Not started
166 | 2026-09-29 | 24 | 6 | 7. Target Hit | Press outreach — podcasts, business blogs covering creator economy | Marketing | P2 | 2 |  | Not started
167 | 2026-09-30 | 24 | 6 | 7. Target Hit | Sign VA for 20hr/week (comment moderation, basic research) | Ops | P1 | 1.5 |  | Not started
168 | 2026-10-01 | 24 | 6 | 7. Target Hit | Onboard VA, document all SOPs | Ops | P1 | 3 |  | Not started
169 | 2026-10-02 | 25 | 6 | 7. Target Hit | Light day with VA handling ops | Rest | P2 | 0.5 |  | Not started
170 | 2026-10-03 | 25 | 6 | 7. Target Hit | Test: fully automated week — you do only strategy, VA + crons handle rest | Ops | P1 | 1 |  | Not started
171 | 2026-10-04 | 25 | 6 | 7. Target Hit | Review results of automated week — feasible to scale or not? | Analytics | P0 | 1.5 |  | Not started
172 | 2026-10-05 | 25 | 6 | 7. Target Hit | Build hiring pipeline for second VA / junior editor | Ops | P2 | 1.5 |  | Not started
173 | 2026-10-06 | 25 | 6 | 7. Target Hit | Retrospective on all 9 channels ranked by $/hour of your time | Analytics | P0 | 2.5 |  | Not started
174 | 2026-10-07 | 25 | 6 | 7. Target Hit | Sunset bottom 2 channels, keep budget focused on top 7 | Ops | P0 | 1.5 |  | Not started
175 | 2026-10-08 | 25 | 6 | 7. Target Hit | Scale the winning formula: +1 channel using proven template | Content | P1 | 3 |  | Not started
176 | 2026-10-09 | 26 | 6 | 7. Target Hit | Launch-day for the new channel — first 3 videos | Content | P1 | 1.5 |  | Not started
177 | 2026-10-10 | 26 | 6 | 7. Target Hit | Observation — first 48 hours of new channel | Analytics | P1 | 0.5 |  | Not started
178 | 2026-10-11 | 26 | 6 | 7. Target Hit | End-of-Phase review: month-over-month net profit trend | Analytics | P0 | 2 |  | Not started
179 | 2026-10-12 | 26 | 6 | 7. Target Hit | $20k/mo milestone check — celebrate or plan the extra push | Analytics | P0 | 1 |  | Not started
180 | 2026-10-13 | 26 | 6 | 7. Target Hit | Draft Year-2 plan: scale to $50k/mo — same formula, more channels | Ops | P1 | 3 |  | Not started